## GANTT chart
| 2021 | [7 empty] | 2022 | [11 empty] | 2023
| MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
Stream data collection | bar: 2021 SEP to 2023 FEB
Oswaldo | bar: 2021 JUL to 2022 JUN
Task |  |  | pwe | pwf | pwb | pwb | pww | pww | pww | tea | tea | tew | tew | mop
Katherine | [14 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: pwb to mop
Task |  |  | srd | srd |  | bpe | bpe | bpe | bpa | bpa | bpa | bpw | bpw | bpw | bbe | bbe | bba | bba | bbw | bbw | sre | sre | sra | sra | srw | srw | srw | data | mop
| PostDoc 1 |  |  |  |  | bpa: PostDoc 2; sre: Both
| pwe | power analysis explatory |  |  |  | bpa: srd; bpa: Hakalau stream design; sre: mop; sra: mop-up of analyses and deliverables
| pwf | power analysis frequentist |  |  |  | bpa: sre; bpa: Hakalau stream data explatory; sre: data; sra: data release
| pwb | power analysis Bayesian |  |  |  | bpa: sra; bpa: Hakalau stream data analysis; sre: Alternative projects and tasks
| pww | power analysis write-up |  |  |  | bpa: srw; bpa: Hakalau stream write-up; sre: uge; sra: ungulate explatory
| tea | trap efficiency analysis |  |  |  | bpa: bpe; bpa: Biocomplexity param. reestimation exploration; sre: uga; sra: ungulate analysis
| tew | trap efficiency write-up |  |  |  | bpa: bpa; bpa: Biocomplexity param. reestimation analysis; sre: ugw; sra: ungulate write-up
[9 empty] | bpw | Biocomplexity param. reestimation write-up | [11 empty] | shc | Hapuu cavity w PJH
[9 empty] | bbe | Biocomplexity bird diagnostics exploration | [11 empty] | ssd | NRPP State dataset w RM
[9 empty] | bba | Biocomplexity bird diagnostics analysis
[9 empty] | bbw | Biocomplexity bird diagnostics write-up